## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | TigerCheck | [6 empty] | Completed | 1
| Team Members: | Nick Bean, Ethan Darby, Zach White, Ross Spears | [6 empty] | Discarded | 2
| Date: | 2014-02-17 | Cycle: | 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | A system for nurses to collect data from health screenings, primarily from local schools | [6 empty] | In Review
Unstarted
| Cycle Intent: | Add more functionality for front page UI, begin work on station forms.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Rework forms to be more readable and be on one sheet |  | 3 | 2 | 0 | Unstarted | 0 | 0
2 | Add BMI to data readout |  | 3 | 1 | 0 | Unstarted | 0 | 0
3 | Rebuild project with focus on future development |  | 3 | 90 | 10 | Collaboration | 20 | 20
4 | Build Station functionality |  | 2 | 30 | 20 | Collaboration | 0 | 0
5 | Add more front page functionality |  | 2 | 30 | 20 | Collaboration | 0 | 0
6
7
8
9
|  |  | Planned Total | 153 | 50 | Actual Total | 20 | 20

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | TigerCheck
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ross Spears | 1,2,4 |  |  |  | 2 | 0 | 0 | 2 | 1 | 2 | 2 | 0 | 0 | 4 | 3
| Zachary White | 1,2,4 | 4 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4
| Ethan Darby | 1,2,4 | 4 |  |  | 4 | 0 | 0 | 1 | 1 | 2 | 2 | 10 | 10 | 13 | 13
| Nick Bean | 1,2,4 |  |  |  | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1
[5 empty] | Totals | 10 | 0 | 0 | 3 | 2 | 5 | 5 | 14 | 14 | 22 | 21
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| n/a | [6 empty] | Add more front page capabilities, begin work on station content
| Obstacles encountered since last status report: | [6 empty] | Notes:
| n/a | [6 empty] | Lorem ipsum dolor sit amet, consectetur adipisicing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Ut enim ad minim veniam, quis nostrud exercitation ullamco laboris nisi ut aliquip ex ea commodo consequat. Duis aute irure dolor in reprehenderit in voluptate velit esse cillum dolore eu fugiat nulla pariatur. Excepteur sint occaecat cupidatat non proident, sunt in culpa qui officia deserunt mollit anim id est laborum.
Risks facing the project:
Lorem ipsum dolor sit amet, consectetur adipisicing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Ut enim ad minim veniam, quis nostrud exercitation ullamco laboris nisi ut aliquip ex ea commodo consequat. Duis aute irure dolor in reprehenderit in voluptate velit esse cillum dolore eu fugiat nulla pariatur. Excepteur sint occaecat cupidatat non proident, sunt in culpa qui officia deserunt mollit anim id est laborum.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | TigerCheck
Member: |  | Ethan Darby
Week Ending: |  | 2014-02-18
Cycle: |  | Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2014-02-04 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | Started work on new program's front page, started work on SQL database
Date: | 2014-02-05 | Result: | SQL database installed, basic menu interface complete
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed: | Built Check-in / check-out functions
Date: | 2014-02-06 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed: | Tested Check-in/out buttons as well as front page
Date: | 2014-02-07 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2014-02-08 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2014-02-09 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed: | Finished testing check-in/out, froze code for presentation
Date: | 2014-02-10 | Result:
Hours Worked: | 3 | Problems encountered:

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | TigerCheck
Member: |  | Nick Bean
Week Ending: |  | 2014-02-18
Cycle: |  | Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2014-02-04 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2014-02-05 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2014-02-06 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed: | Wrote written report for architectural spike
Date: | 2014-02-07 | Result: | Content of report complete
Hours Worked: | 3 | Problems encountered: | Not quite sure on required format for report
Day: | Saturday | Task(s) performed: | Cleaned up report, added more content, Started powerpoint
Date: | 2014-02-08 | Result: | Finished report and powerpoint
Hours Worked: | 4 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2014-02-09 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2014-02-10 | Result:
Hours Worked: | ? | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | TigerCheck
Member: |  | Zach White
Week Ending: |  | 2014-02-18
Cycle: |  | Spike
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2014-02-04 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2014-02-05 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed: | Wrote code for check-in button
Date: | 2014-02-06 | Result: | Check-in button was complete, untested
Hours Worked: | 3 | Problems encountered:
Day: | Friday | Task(s) performed: | Wrote code for check-out button
Date: | 2014-02-07 | Result: | Check-out button was complete, untested
Hours Worked: | 3 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2014-02-08 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2014-02-09 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed: | Cleaned up code, fixed minor bugs
Date: | 2014-02-10 | Result: | Check-in/check-out tested and most bugs found. Check broad cases
Hours Worked: | 1.5 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | TigerCheck
Member: |  | Ross Spears
Week Ending: |  | 2014-02-18
Cycle: |  | Spike
Team Member Work Summary
Day; | Tuesday | Task(s) performed: | Talked with Dr. Qin regrading lack of viable work for the project
Date: | 2014-02-04 | Result: | Tasked with redoing TigerCheck with focus on readability
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2014-02-05 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed: | Met with group, started work on forms for presentation. With group, adjusted design to comply more with ideas
Date: | 2014-02-06 | Result: | New Design drawing, mild reworking of how code will work/flow
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed: | Met with group, continued working on forms for presentation
Date: | 2014-02-07 | Result: | Most forms completed
Hours Worked: | 3 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2014-02-08 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2014-02-09 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed: | Met with group, completed powerpoint and report with Nick
Date: | 2014-02-10 | Result: | Powerpoint and report complete
Hours Worked: | 2 | Problems encountered: